## D5
D5 — Vulnerability Remediation Tracking
SWIFT CSCF Controls: 2.7 (Vulnerability Scanning) ¦ 7.3A (Penetration Testing — Advisory) ¦ Tracking log for all D4 scan findings and D6 pen test findings
Evidence Type: Tracking Log ¦ Mandatory Status: Mandatory (M) for scan findings ¦ Advisory (A) for pen test findings ¦ SWIFT CSCF Assessment Test Sample Data
Evidence Field / Assessment Area | 100% Accuracy — Full Compliance | 75% Accuracy — Partial Compliance | 50% Accuracy — Material Gaps
Compliance Verdict → | ✔ PASS — Evidence Complete & Fully Controlled | ⚠ PARTIAL — Evidence Present with Notable Gaps | ✘ FAIL — Significant Deficiencies / Absent Evidence
▶ TRACKER METADATA
Tracking Log Reference & Tool | SWIFT-VULN-REMEDIATION-TRACKER-v3.2.xlsx ¦ Storage: SharePoint /Compliance/SWIFT/D5-Remediation/ ¦ Scope: all D4 scan findings (Qualys VMDR) + all D6 pen test findings (Pentest Report 2024) ¦ Maintained by: IT Security Manager (John Malik) — updated within 5 business days of new scan results ¦ Review cadence: weekly status update in patching governance meeting; CISO briefing monthly ¦ Qualys VMDR integration: findings auto-imported via API — manual fields (owner, risk acceptance, pen test findings) added manually ¦ Total tracked findings (all time, open): 42 scan findings + 12 pen test findings | Vuln_Remediation_Tracker.xlsx ¦ Maintained by IT Operations Lead (Sarah Chen) ¦ Updated after each scan and pen test. Qualys findings manually exported and pasted. Pen test findings: partially transferred from pen test report. Review: ad-hoc. | No formal remediation tracker. Scan report (PDF) filed in SharePoint. Findings noted informally in email. No structured tracking, no owners, no target dates.
▶ SCAN FINDINGS REMEDIATION — CRITICAL (CVSS 9.0+)
Current Open Critical Findings | 0 critical findings currently open. All previously identified critical findings remediated within 1-month SLA. Last critical finding: QID 91819 (Windows Kerberoasting exposure on SWFT-SRV01) — identified 18 Feb 2025, remediated 25 Feb 2025 (7 days) via Group Policy change (krbtgt password rotation + Kerberos delegation restrictions applied). Confirmation: Qualys re-scan 26 Feb 2025 confirmed QID 91819 absent on SWFT-SRV01. Evidence: re-scan report + Group Policy change management record (CHG-20250225-GP-001) archived. | 0 critical findings currently open. 2 critical findings identified in Sep 2024 scan. Both remediated: (1) Kerberoasting: resolved via Group Policy (Oct 2024, 15 days — within SLA); (2) Oracle Java on SWIFT-PC-03: Java uninstalled (Oct 2024, 18 days — within SLA). Re-scan confirmation: performed for 1 of 2 (Qualys re-scan). Java removal: confirmed via SCCM software inventory (no re-scan). | 7 critical findings currently open from August 2023 scan (18 months old): CVE-2024-21413 (Outlook RCE, operator PCs — CVSS 9.8), CVE-2024-50395 (FortiGate — CVSS 9.6), CVE-2024-50379 (Apache Tomcat — CVSS 9.8), CVE-2024-38021 (MS Office — CVSS 9.8) on servers, VMware ESXi ESC-50 vulnerability, 2 additional Windows critical CVEs. ALL OVERDUE — oldest 18 months past identification. No owner assigned. No remediation action taken. No CISO awareness confirmed.
Critical Finding SLA Compliance (Last 12 months) | Critical findings identified in period: 3 ¦ Resolved within 1-month SLA: 3 of 3 (100%) ¦ Average resolution time: 11 days ¦ Oldest resolution: 19 days (HSM management interface critical finding — required nCipher TAM coordination) ¦ Risk acceptances for critical: 0 ¦ SLA COMPLIANCE: 100% | Critical findings identified: 5 ¦ Resolved within 1-month SLA: 4 of 5 (80%) ¦ 1 critical finding (CVSS 9.0, ESXi misconfiguration) resolved in 38 days (8 days overdue) — IT Security Manager approved deferral due to vSphere maintenance window constraint; compensating control (network isolation of affected VM) documented | Critical findings identified: 7 ¦ Resolved within 1-month SLA: 0 of 7 (0%) ¦ All 7 critical findings remain open 18+ months after identification ¦ No escalation to CISO ¦ No risk acceptance ¦ No compensating controls ¦ SLA COMPLIANCE: 0%
▶ SCAN FINDINGS REMEDIATION — HIGH (CVSS 7.0–8.9)
Current Open High Findings | 3 high findings currently open (all from Feb 2025 scan — within 3-month SLA): (1) QID 372100 — TLS 1.0 on SWFT-SRV01 IIS ¦ Owner: Sarah Chen ¦ Target: 01 March 2025 ¦ Status: In Progress (registry change tested in staging, awaiting CAB approval scheduled 01 Mar 2025); (2) QID 91714 — SMBv1 on JUMP-01 ¦ Owner: Raj Kumar ¦ Target: 01 March 2025 ¦ Status: Remediated 28 Feb 2025 (GPO applied), re-scan scheduled 03 Mar 2025; (3) QID 45038 — FortiGate management interface exposure ¦ Owner: Raj Kumar ¦ Target: 15 March 2025 ¦ Status: In Progress (firewall rule change drafted, CAB 15 Mar) | 6 high findings open: 2 from Feb 2025 scan (within SLA), 4 from Sep 2024 scan — 2 within SLA (6-month window for 2 low-priority config findings), 2 slightly overdue: QID 88213 (SWFT-SRV02 IIS config) overdue by 3 weeks — IT Security Manager approved deferral to coincide with planned server maintenance Q1 2025; QID 45192 (network service exposure) overdue by 1 week — active remediation, expected completion 05 Mar 2025. | 19 high findings open — all from August 2023 scan: 12 unpatched CVEs (all >6 months overdue beyond 3-month SLA), 4 software vulnerabilities (outdated Java, .NET), 3 network exposure findings. None with assigned owners. None with target dates. No escalation. No risk acceptance for any finding.
High Finding SLA Compliance (Last 12 months) | High findings in period: 12 ¦ Resolved within 3-month SLA: 11 of 12 (92%) ¦ 1 deferral with formal risk acceptance: QID 91033 (Windows RPC service exposure, CVSS 7.5) — service required by legacy application, compensating control (SWIFT zone firewall rule restricting RPC to specific hosts) documented; CISO-approved risk acceptance valid until Q3 2025 ¦ Average resolution time: 34 days | High findings in period: 15 ¦ Resolved within SLA: 12 of 15 (80%) ¦ 3 overdue: all with informal IT Security Manager approval but no formal risk acceptance process applied ¦ Average resolution: 52 days | High findings: 19 open ¦ Resolved within SLA: 0 of 19 ¦ Average age of open findings: 14+ months ¦ No SLA tracking ¦ No formal risk acceptance for any finding
▶ RISK ACCEPTANCES
Formally Risk-Accepted Findings | 2 active risk acceptances (scan findings): (1) QID 91033 — Windows RPC service exposure (CVSS 7.5) on SWFT-SRV01 ¦ Business justification: legacy SAP connector requires RPC over named pipes; vendor roadmap for REST API migration expected Q3 2026 ¦ Compensating control: SWIFT zone firewall ACL restricts RPC to SAP server IP only (FW-01 rule ACL-SWIFT-015) ¦ Approver: CISO Jane Reeves ¦ Approval date: 15 November 2024 ¦ Review date: 15 May 2025 (6-month review cycle) ¦ (2) QID 45038 — FortiGate mgmt interface exposure ¦ Interim acceptance while CAB-approved firewall change is scheduled ¦ Approver: IT Security Manager ¦ Approval: 20 Feb 2025 ¦ Review: 20 Mar 2025 (30-day interim only) | 3 risk acceptances: 2 with IT Security Manager approval (not CISO — below expected authority level for scan findings). 1 with CISO approval. 1 risk acceptance has no defined review date — indefinite acceptance not compliant with policy. | 0 formal risk acceptances — findings simply not remediated without any documentation. No risk acceptance form exists. No approval process. Findings are effectively implicitly accepted by inaction, without any accountability.
▶ PENETRATION TEST FINDINGS TRACKING
Pen Test Findings Tracker Overview | Pen test findings from D6 (Pentest Report: PT-2024-SWIFT-001, conducted October 2024 by Bishop Fox) fully tracked in D5 tracker: 12 findings total (2 critical, 4 high, 4 medium, 2 low). All findings have: finding ID, severity, affected component, description, recommended remediation, assigned owner, target date, status, retest result. Critical and high finding remediation priority: target 30 and 90 days respectively from report delivery date. | Pen test findings (12 total from 2023 pen test) partially tracked. 9 of 12 findings in tracker. 3 low/medium findings not transferred from report. Critical and high findings tracked with owners. 2 medium findings: no owner assigned. | 0 pen test findings tracked in any log. Last pen test report (2022) filed as PDF — no findings extracted to a tracker. Remediation status of pen test findings: completely unknown. No owner. No target date. No retest ever performed.
Pen Test Critical/High Findings Remediation Status | Critical findings (2): Both remediated and retested. (1) PT-2024-001-C1: "Kerberoastable service account with weak SPN password" — remediated via service account password rotation + removal of unnecessary SPN (Raj Kumar, 05 Nov 2024, 14 days from report). Retest: Bishop Fox remote retest 20 Nov 2024 — confirmed resolved. (2) PT-2024-001-C2: "SMBv1 relay attack path from JUMP-01 to SWIFT servers" — remediated via SMBv1 disable GPO + NTLM restriction (01 Dec 2024, 40 days from report). Retest: 10 Dec 2024 — confirmed resolved. Both critical findings fully closed. | Critical findings (1): "Weak TLS configuration on SWFT-SRV01" — remediation in progress (TLS 1.0 disabled in staging, pending production deployment). Target: 28 Feb 2025. High findings (3): 2 remediated, 1 in progress (target Mar 2025). Retest: not yet performed — scheduled for March 2025 post-remediation. | 2022 pen test critical finding ("Default admin credentials on HSM management interface") — status unknown. No record of whether remediated. No retest. 3 high findings from 2022 report — all unknown status. Assessors note: 2 of the 2022 pen test high findings match current open scan findings — likely the same vulnerabilities identified repeatedly across cycles.
Pen Test Retest Results | Retests completed for all remediated critical and high findings: (1) PT-2024-001-C1 retest: Bishop Fox remote retest 20 Nov 2024 — scope: Kerberoastable accounts in SWIFT AD OU. Result: no Kerberoastable accounts found in SWIFT OU. Report addendum issued (REF: PT-2024-001-RETEST-R1). (2) PT-2024-001-C2 retest: Bishop Fox remote retest 10 Dec 2024 — scope: SMBv1 relay path from JUMP-01. Result: SMBv1 confirmed disabled via Nmap probe; NTLM relay path blocked. Medium/low findings: internal retest performed by IT Security Manager (not independent). Retest evidence: screenshots + Nmap output archived. | Retest: scheduled for March 2025 post-remediation of outstanding findings. No retest yet performed. Previous pen test (2023): no retest evidence on file. | No retests ever performed. No retest planned. Organisation unaware that retest of pen test findings is expected. 2022 pen test final report is the only evidence — no addendum, no retest report.
Pen Test Findings Feeding Into Security Update Process | Formal feedback mechanism (documented in patching governance process): (1) All pen test findings cross-referenced against current patch register — findings linked to specific CVEs are tracked in both D5 and D3 patch deployment log; (2) Pen test findings requiring configuration changes added to IT hardening backlog (reviewed monthly at patching governance meeting); (3) New vulnerability classes identified in pen test added to Qualys VMDR custom policy to ensure future scans detect regression; (4) Last cycle: SMBv1 finding from pen test led to addition of QID 91714 to standard SWIFT scan policy — detecting SMBv1 across all in-scope systems going forward. | Pen test findings that involve patching are added to the patch register manually by IT Security Manager. Configuration findings tracked separately in an action log. No formal integration into scan policy. Ad-hoc process. | No formal mechanism. Pen test findings and vulnerability scans are treated as completely separate activities. No cross-referencing. Patch register does not reference pen test findings. Same vulnerabilities re-identified in scan and pen test independently.
▶ SUMMARY METRICS
Remediation Metrics Dashboard | Total open findings: 42 (3 high, 14 medium, 22 low, 3 within SLA ¦ 0 critical open) ¦ Total pen test findings: 12 (all critical/high closed; 2 medium in progress) ¦ Average time to remediate critical: 11 days ¦ Average time to remediate high: 34 days ¦ Risk acceptances active: 2 (both with CISO/IT Security Manager approval and review dates) ¦ Findings introduced (last 30 days): 6 (all from Feb 2025 scan) ¦ Findings closed (last 30 days): 4 ¦ Trend: remediation backlog decreasing (from 48 to 42 over last quarter) | Open findings: 29 (0 critical, 6 high, 18 medium, 5 low) ¦ Pen test findings: 12 (1 critical in progress, 3 high — 2 closed 1 in progress) ¦ Average time to remediate high: 52 days ¦ Risk acceptances: 3 (1 CISO-approved, 2 IT Security Manager-approved) ¦ Retest pending: 5 findings | Open findings: 61 (7 critical, 19 high, 33 medium, 2 low — all from 18-month-old scan) ¦ Pen test findings: not tracked ¦ Average time to remediate: incalculable — 0 findings remediated ¦ Risk acceptances: 0 ¦ Owner assignment: 0 findings have assigned owners ¦ Escalation: no findings escalated to CISO ¦ Overall: CRITICAL non-compliance
SWIFT CSCF Test Sample Data — D5 ¦ Three accuracy tiers: 100% (Full Compliance), 75% (Partial), 50% (Material Gaps)