## Vuln Scan Report
Finding ID | Scan Date | System | CVE | Severity | CVSS Score | Plugin/Check | Description | Status | Remediation | Target Date | Closed Date
VUL-001 | 2024-10-10 | SAA Server | CVE-2024-1234 | Critical | 9.8 | Nessus #112233 | Remote code exec in SMBv1 | Remediated | Disabled SMBv1 | 2024-10-15 | 2024-10-13
VUL-002 | 2024-10-10 | Alliance Gateway | CVE-2024-5678 | High | 8.1 | Nessus #223344 | OpenSSL vuln | Open | Patched OpenSSL 3.0.7 | TBD
VUL-003 | 2024-10-10 | Jump Server | CVE-2024-9012 | Medium | 5.4 | Nessus #334455 | Weak TLS config | Remediated | Enforced TLS 1.2+ | 2024-10-25 | 2024-10-22
VUL-004 | 2024-10-10 | SIEM Server | CVE-2024-3456 | Low | 3.1 | Nessus #445566 | Banner disclosure | Open | Removed service banner | TBD
VUL-005 | 2024-10-10 | SAA Server | CVE-2024-7890 | High | 7.5 | Nessus #556677 | Outdated Java runtime | Remediated | Updated JRE to 17.0.8 | 2024-10-20 | 2024-10-19
VUL-006 | 2024-10-10 | Firewall FW-01 | CVE-2024-2345 | Medium | 6.3 | FortiScan | Admin panel exposure | Remediated | Restricted mgmt access | 2024-10-28 | 2024-10-25