## Vuln Remediation
Tracking ID | CVE | System | Severity | Identified | SLA Days | Target Date | Actual Close | Owner | Status | Verification | Notes
REM-001 | CVE-2024-1234 | SAA Server | Critical | 2024-10-10 | 3 | 2024-10-13 | 2024-10-13 | Patch Admin | Closed | Verified by scan | Within SLA
REM-002 | CVE-2024-5678 | Alliance Gateway | High | 2024-10-10 | 7 | 2024-10-17 |  | Pending | Open | Not yet verified | 1 day late
REM-003 | CVE-2024-9012 | Jump Server | Medium | 2024-10-10 | 30 | 2024-11-09 | 2024-10-22 | Sec Engineer | Closed | Verified by scan | Ahead of SLA
REM-004 | CVE-2024-3456 | SIEM Server | Low | 2024-10-10 | 90 | 2025-01-08 | 2024-10-28 | Sec Engineer | Closed | Verified | Ahead of SLA
REM-005 | CVE-2024-7890 | SAA Server | High | 2024-10-10 | 7 | 2024-10-17 |  | Pending | Open | Not yet verified | 2 days late, accepted
REM-006 | CVE-2024-2345 | Firewall FW-01 | Medium | 2024-10-10 | 30 | 2024-11-09 | 2024-10-25 | Network Ops | Closed | Verified | Within SLA